## Overview of Timetable
June |  |  |  | July |  |  |  | August |  |  |  | Sep
wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4
Questionnaire (Requirements) & Prototypes background research Start Group Report |  | Sprint 1 |  | feedback on 1st sprint Revise and reflect | Sprint 2 |  | feedback on 2nd sprint Revise and reflect | Sprint 3 Code Testing (Integration etc..) Users Test Optimization Start Individual report |  | Finished our project at end of Aug | Submission | Due 5th,Sep

## Timetable by week
wk17 | [6 empty] | wk18 | [6 empty] | wk19 | [6 empty] | wk20
2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02
Start | Project Timetable |  |  | *Questionnaire *Programming language *Possible Functionalities *Prototyping Project Proposal *Evaluation Plan *Use case diagram *Start Group Project |  |  |  |  | Collecting & Analyzing collected data from Questionnaire |  | *a workable use case diagram * Decide programming languages *Send for approval for requirements base on questionnaire *Send for approval for prototype |  |  | SPRINT 1
wk21 | [6 empty] | wk22 | [6 empty] | wk23 | [6 empty] | wk24
2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30
1st sprint results check | [6 empty] | Sprint 2 | [13 empty] | checking 2nd sprint
wk25 | [6 empty] | wk26 | [6 empty] | wk27 | [6 empty] | wk28
2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06 | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27
Start Individual Report | Sprint 3 | [12 empty] | Finalising Group Report & Individual Report | [10 empty] | Hand In Report
wk29 | [6 empty] | wk30
2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10
buffer week for project improvement

## STP shortlisted project 2023
MSc Computer Science Summer Team project - Supervisor project preference
Full project list can also be seen as a word document here
ID | Project Title | Proposal Text | Organisation | Supervisor First choice | Supervisor Reserve(s)
1 | Emerging technology Learning game | 1) What is the key issue that motivates the need for the project? There are a number of technologies that are currently revolutionising the way that business operates and will Impact society significantly. It Is Important for students from all disciplines to be aware of the Impact of these technologies - without the learning experience seeming challenging. We would like to create a game that helps people/encourages people to learn about these technologies 2) What part of the key issue is going to be addressed? Create a game inspired by Star Trek Adversaries - where the player must explore the galaxy in their space craft. Exploring the galaxy unlocks buffs for the ship and lays claim to the territory for the players empire. The user can collect Power Cards which add new shields, better sensors etc to their ship - but to unlock those cards - the player needs to answer questions around a number of technologies. In the first instance the questions will be very high level and will come from this learning experience - https://students.yourlearning.ibm.com/activity/PLAN-91F302DE9BBD?utm_source=skillsbuild.org&_ga=2.268459121.1039652570.1658212605-1983854700.1656655509 Questions will cover the main aspects of AI, Cybersecurity, Cloud, Blockchain, IoT and DataScience - effectively when these methods and technologies such be used - these will be multiple choice questions presented to the user As the player progresses in the game and deeper into the galaxy the questions will become more specialised and require the player to learn from the specific AI badge, the IoT Badge etc - all of which can be found here - https://skillsbuild.org/students/course-catalog Ideally this would be a multiplayer game - where players compete for own empires - while the gain practical skills 3) How will you validate your success? Frequent check In with the stakeholder - IBM mentor 4) Technologies IBM Cloud and Watson will be useful for this. | IBM |  | Ruzanna Chitchyan
2 | University Watson AI Avatar | 1) What is the key issue that motivates the need for the project? Coming to university can be an exciting but also challenging experience for new students. Much In the same way that a new employee needs to be onboarded by an organisation, a student must learn about the university and how to engage effectively. A lot of this Is done through Word of Mouth and via the help of faculty. What If though - each student had access to their own A.I university advisor that would help them find their feet during the first few weeks at university? 2) What part of the key issue is going to be addressed? Create a web app Watson chatbot that the students (users) can access via a QR code from their mobile device. The QR code could be printed out and left at strategic areas around the university for new students to see. The chat bot would provide Information that a university student wished they knew when they first arrived at your university. The content of the chatbot could be targeted to serve the students of a particular course - or It could be usable by every university student at your university. Content can Include - what are the Important things to do when you first come to university - where can I find books and resources - what communities are there that I can join to make friends - If I am having difficulties - where can I go for help? I would also like to Include a Life Skill as part of the watson chatbot - In this case Design Thinking - as this is a fundamental Problem Solving skill and will also provide each student with a recognised IBM Accreditation In Design thinking - https://skillsbuild.org/students/course-catalog/design-thinking Also have the chatbot link to mental health resources such as Mindfulness - https://skillsbuild.org/students/course-catalog/mindfulness This Is particularly useful If the user Is showing signs of stress when engaging with the chatbot 3) How will you validate your success? It Is expected that the team will validate their application, by having fellow students testing the tool, providing feedback throughout the development cycle. Students are one of our main stakeholders - and so their opinion Is valuable to the success of this project. 4) Technologies IBM Cloud and Watson will be useful for this. | IBM | Nirav Ajmeri
3 | Skills Enablement Game | learning can be a solitary experience - and also In the short term a potentially challenging experience too. To help and encourage people to avail themselves of learning experiences that will enrich their lives - we need to make learning more fun, engaging and collaborative 1) What part of the key issue is going to be addressed? Create a city building game In the form of a web app - where the user builds elements of their city by completing learning experiences. Each specific learning experience will offer a boost or 'buff' to the city. So for example - completing Agile and Design Thinking learning experiences will allow the city to progress at a faster rate (In terms of building facilities for the population). Whereas AI and Automation could reduce cost of goods and Items - making the population happier In the game there will be other cities being built - either by AI or other players. If one city progresses beyond the other cities - then the population will slowly move from other cities Into the more advanced one. This In turn will provide the resources for the city to grow and build new capabilities The winner of the game Is the city which has the most population (or all of the population) on the map. Learning experiences are to be taken from: Skills Build https://skillsbuild.org/ IBM Academic Initiative https://www.ibm.com/academic/home to test whether a user has successfully completed a learning experience the game will ask questions to test the knowledge of the user. Once the questions are answered the new capability will be unlocked For Inspiration on the look of the game - review games such as Tribal Wars 2) How will you validate your success? It Is expected that the team will validate their application, by having fellow students testing the game and play it, providing feedback throughout the development cycle. Students are one of our main stakeholders - and so their opinion Is valuable to the success of this project. 3) Technologies Recommend using IBM Cloud and also Incorporating IBM Watson to support enhanced Interaction with the user. The game could for example 'speak' to the player to guide them. In terms of the game engine - there are many free open source game engines to choose from | IBM | David Bernhard | Nirav Ajmeri
4 | AR AI Art | Create an application that will allow a user to build Augmented Reality AI Art Utilise Augmented Reality and Watson to create a unique piece of interactive art. Use Watson to allow the user to interact with the art via speech and allow the art to talk back to the viewer This is a pioneering type project - art is very subjective - would really suit a technologist with an interest in art Inspiration: https://www.linkedin.com/posts/ajjames_would-you-visit-an-augmented-reality-art-activity-6849197789449093120-zQia/ | IBM |  | Andrew Calway
5 | Boat state estimation from image analysis | We are the UK entry for the Americas Cup, the longest continuously running sport competition in the world. We are currently designing a boat for the 37th edition of the event, a foiling monohull due to compete in Barcelona, 2024. More details on the boats can be found here: https://www.youtube.com/watch?v=OQsXDdGxk3U A key component in the campaign is to predict the performance of other teams, and reconnaissance of the boats is provided in the form of pictures and videos. Our project proposal is to develop a system to estimate the boat state from a series of images, such as attitude, roll, foil size, and sail settings. This information will help accelerate our learning of the competitor performance, and give us a great tool to use during the remainder of this campaign. The minimum viable product would include: - Creation of a GUI for image loading and manipulation - Users can select and measure features within the images The ideal system would also: - Use automated feature extraction to avoid user input - Process videos and series of images - Also link to a GPX track to monitor images over time | Ineos Britania | Michael Wray | Andrew Calway
6 | Simple mmWave Radar and vision fusion. | TI's mmWave sensors are well integrated, low-power, and optimal BOM devices for their capability. When it comes to the radar chip processing capabilities, the platform which combines hardware, software examples, and tools is already popular with our customers. However there are competitive technologies in the market and often TI mmWave sensors are compared negatively when it comes to angular resolution which is related to the number of virtual antennas that are supported per device. So what are the options for addressing this customer concern ? This project will be a continuance some work that TI has already started on the topic of fusing radar with a cmos vision sensor. A demonstration based on a TI mmWave SoC evaluation module (IWR6843AOPEVM), some PC based python code, and basic USB webcam is already available. The goal of this student project would be to: 1) Use OpenCV or ML to detect corner reflectors, or test objects for segmentation of the image. 2) Use ML to better map radar onto camera image given the lens/focal length unknowns 3) Annotate depth / speed to projected objects 4) Utilise a tracker to better predict the trajectory of moving objects. 5) Using beaglebone AI-64, implement the existing PC based python code as embedded function, with a webserver as the UI. mmWave radar board and webcam will interface to the beagebone. | Texas Instruments |  | Michael Wray
7 | Facilitating better responses to disclosures of child sexual abuse NOTE: this is an individual project with external client | My work is concerned with non-recent child sexual abuse, silences and silencing, and the creative resilience of survivors. I would like to co-produce an app with victims and survivors of non-recent child sexual abuse to talk people through how to respond to disclosures of child sexual abuse. Victims and survivors frequently relate inadequate and inappropriate responses to disclosures, and this app would work to talk users through the processes of receiving and acting on disclosures. It would also hopefully include signposting to relevant local support services including SARCs (Sexual Abuse Referral Centres), counselling, and therapeutic services. The app would be co-developed with victims and survivors, and would be intended for: emergency and healthcare professionals (as they are frequently the first to receive disclosures); teachers in secondary and higher education; and parents groups. The app would be accompanied by a teaching toolkit that would be used to teach and talk about issues relating to child sexual abuse. Users could download the app onto their phones and work through an example disclosure to understand the barriers faced by victims and survivors, and the ways in which they can facilitate disclosures and respond appropriately in the future. I will be applying for funding in order to support a steering group including victims and survivors and specialists (counsellors, therapists, and activists) who would work to co-produce the app and provide critical reflection as the project develops. This funding could also contribute towards dissemination and 'scaling up' of the concept in the future, in collaboration with the Computer Science team if appropriate. | UoB | Ossama Metala | David Bernhard, Nirav Ajmeri
8 | Machine-Readable Legislation (MRL) | Machine-Readable Legislation (MRL) Machine-readable legislation (MRL) is developed by creating the text for legislation or policy simultaneously with the computer code that will be used to implement them. Through concurrent development, technical challenges to the implementation of policy are reduced; however, systems must be built in a modular approach that allows for the implementation of this business logic. MRL enables governments to implement a more consistent and equitable application of the law. Requirement We would like to understand how MRL could be implemented and applied to Defra group activities so that legislation could be implemented in a faster, clearer and more efficient manner available to all. But also would like to understand what restrictions there are to implementing it in code. Which legislation is harder to produce as code. We would like to see the machine readable code structure, how it could be expanded for different types of legislation, such as warning levels, high/low levels, guidance levels etc. We would also like to see a documented and predefined “tagging” structure e.g. “policy_name”, “'legal_limit” etc, that could be used for whatever legislation is required now and in the future, so it should be extendable. We would like to see a working prototype for different types legislation that Defra group is responsible for (Environment Agency, Natural England, Maritime Agency, Animal Plant Agency, etc) so that we could see in the code the relevant legislation and its criteria's for say forestry, water, maritime, air, etc. We would then like to be able to query this legislation (via some sort of interface, i.e. browser, chatbot, etc- user, api - remote application) to determine if the activity was legal or illegal. Whichever method is chosen it should use the same interface so that the service could be extended to new devices and applications in a very simple way. For example, legal limit for extracting river water per day is 10,000 litres etc, how could this be represented in machine code, how could this be queried, how could it maintained and version controlled etc. We would like the project to be delivered in an Agile iterative manner, delivering little and often to gain most value and feedback as quickly as possible, thus allowing any issues to be addressed as soon as possible. We would like to have an over project summary explaining the opportunities and challenges to MRL and a set of recommendations on the back of the work. Background Reading Why This Is Important MRL ensures policy is designed and implemented as intended, reflected in subsequent administrative rules and automatically carried out by various systems. Implementing laws as computer programs is often difficult, as laws are not necessarily written with binary logic in mind. However, the policy is the technology and technology is the policy and the two are inseparable in a digital society. Society will benefit as systems across industries are implemented in a more consistent manner. Business Impact Implementing MRL will be a cross-disciplinary activity, requiring the necessary skills in policy and IT shops, technology implementation and ecosystem engagement to ensure the developed “business logic” is created and used to improve the regulatory process and promote economic benefits. MRL will be a fundamental technical element in creating a composable government to support a digital society by making the writing of laws more data-driven and their implementation more consistent. Drivers As an emerging innovation, the drivers for MRL are more aspirational than concrete. However, there are a number of existing challenges that governments face in the transition to digital government that can be addressed through the implementation of MRL. • The gap between legislative intent and implementation. By implementing MRL, the room for interpretation of legislative or executive intent is eliminated from the process, instead making the law that | DEFRA (Department for Environment, Food and Rural Affairs | Inah Omoronyia | Ruzanna Chitchyan
9 | HE Assessment Tracking Tool (HEAT Tool) | A potential criticism of how the programmes present assessments to students is that it can be opaque and whilst detailed thought with regard to how they link throughout the year has often been conducted, there is no tool available that presents this to either staff or students. Occasionally there are the clustering of deadlines, although frequently this is unavoidable the ability to clearly see this on an infographic at the start of the year would be invaluable for students to manage time and staff to manage expectations. Another pedagogically relevant function of the software would be to map the feed in from formative assessments to that of summative ones along with where summative feedback may have application to future assessments. If this could be hyperlinked back to the actual locations where the feedback is held would be an extremely powerful learning tool to enhance the application of feedback to learning. The ability to see these links in one location would be invaluable to both staff and students. There will be opportunities to work with senior members of both the institution and senior members of the Curriculum Enhancement Project to help develop this strategic tool. | UoB | Simon Lock
10 | Sound Sculpture Application - note will need access to a 3d Printer | 1) What is the key issue that motivates the need for the project? There are many people who are Incredibly creative - but without sight, which limits the creative mediums they can easily enjoy such as painting, drawing and sculpture. This objective of this project Is to change that - and provide a way for people without sight to be able to create their own sound sculptures, which will be unique to them and with the use of AI will Incorporate tones and feelings Into the object. As this piece of art will be a sculpture/3d physical object It can both be created and enjoyed by the artist. 2) What part of the key issue is going to be addressed? We are going to utilise the voice of the creator to build our 3d sculpture. So this project will allow a user to record a 30 second description of a scene, person, object (this could be ' a sunny day' or 'my father' or 'my childhood' for example) . Here we will use the waveform Image of the recording as the basis for the model of our sculpture - but we will also add an extra element. This extra element will use Watson Tone Analyser to analyse the voice recording - and we will use the output of that analysis to provide an extra dimension to the sculpture. Here the waveform will provide the X,Y dimensions (length and height) while the tone analysis will be used to define the Z (width). Once completed the application you create will Input a users voice and output a schematic for a 3d printed scultpure that will show not only a physical representation of the voice description, but also the tone and emotion contained within It. In fact It will be possible for the viewer to Identify the emotions contained within this sculpture Extra - Is It possible to take a picture of the waveform sculpture and recreate the voice description audibly? 3) How will you validate your success? Frequent check In with the stakeholder - IBM mentor 4) Technologies IBM Cloud and Watson will be useful for this. Access to a 3d printer | IBM
11 | Evaluate/develop data storage, LMS platforms and online virtual training software;- To deliver digital virtual education programmes | PROMPT Maternity Foundation (PMF) is a UK charity that delivers training to reduce poor outcomes during childbirth and provide training in the UK and Internationally. We develop training materials and teach multi professional teams of trainers (Midwives, Obstetricians, and Anaesthetists) in hospital maternity units to deliver the emergency training to their own staff. COVID meant we were unable to deliver training in person and had to develop a virtual training package delivered online using Teams or Zoom. This training has worked well and we would like to further develop our ability to deliver the training in the UK and internationally. We have a website (https://www.promptmaternity.org) and at the moment are using a basic LMS to allow download of teaching materials. We are a small charity involving medical professionals and whilst having a grasp of basic computer we really need assistance in understanding the rapidly expanding digital world. We wish to explore the options for the storage of the training materials which allows them to be viewed and downloaded (manuals and videos). We also plan to use a platform to deliver live virtual training involving prerecorded and live events online. Our project would involve looking at the platforms we are using now and reviewing what is available in the ever expanding market for online training packages. the outcome may be there are better commercial programmes/platforms etc out there, or we may need to develop out own programme/website. We have not specified which project team but are keen to look at this over the winter and therefore the undergraduate group would suit us. If however you feel a postgraduate would be better to get involved we would be happy to take your advice. | PROMPT Maternity Foundation - A UK charity based out of Southmead Hospital in Bristol. | Jon Bird | Aisling O'Kane, Ruzanna Chitchyan
12 | A Web Application to Support the Decolonisation of the Psychology Curriculum | Project Description: The University of Bristol has identified decolonising the curriculum as a strategic and ethical priority. In the School of Psychological Science, where we are based, the Equity, Diversity and Inclusion Committee (EDIC) has called on the school to do more to ensure the representation of non-European research and researchers in the curriculum, and help students reflect critically on the social, historical and cultural contexts in which psychology knowledge is produced, disseminated, and used. We would like to develop a web app to help meet these goals locally, as well as support broader, discipline-wide global efforts to decolonise the psychology curriculum. We would like the web app to interface with one or more major academic databases to extract key contextual (e.g., location, gender etc. of the lead author; location and ethnic composition of the sample) and methodological (e.g., type of analysis) details from published psychology papers, and organise them into a searchable application. Such an application could then be queried by educators seeking to introduce greater diversity into their teaching materials, as well as address questions about the nature of psychological knowledge production across time and context. Restrictions: We anticipate working with the team of Computer Science MSc students to define the nature and scope of this project, such that it iterates toward our aims (as briefly outlined above) whilst helping the students meet the learning outcomes for their course. Additionally, the MSc students will form a core part of a multi-disciplinary team and develop insights into current pedagogic best practice. Technical implimentation [NOTE ADDED BY TB] It is expected that students will explore the use of SCOPUS API for the extraction of data from their datatabse. IP issues will be considered and presented as part of this project. The student team will make use of the University's subscription to this service to gain a developer API key. Terms of this license must be complied with. IP Issues: We imagine the direct outcomes of this project (i.e., the web app and supporting documentation) as being open source and open access. There are likely to be IP issues associated with extracting and ‘republishing’ data from academic databases which will need to be resolved prior to commencement of the project. If the web app achieves its stated aims, it will likely be used to support a range of research activities, which will then be written up as journal articles and presented at conferences. It is assumed that, if the MSc students meet the standard requirements for authorship, they will be listed as co-authors. Such matters will be discussed during the planning stages of the project. Us and our organisation: Dr Peter Allen (Senior Lecturer), Dr Chris Kent (Associate Professor) and Dr Polly Barr (Lecturer) are academic staff members in the School of Psychological Science at the University of Bristol. The School of Psychological Science is home to about 45 academic staff members and over 900 students. We are based in and around 12a Priory Rd, Bristol. | University of Bristol | Aisling O'Kane | Nirav Ajmeri
13 | Estate Asset Digital Twin | To create a digital twin of an existing estate utilising 3D BIM (Building Information Modelling), AR, VR, and asset management software to provide live up to date data of client's property portfolio. The University of Bristol Campus could be used as an example project, subject to obtaining approval. A Digital Twin would enable client's to monitor the performance and costs of each individual building, room, or the entire estate. Data could include life cycle condition/cost of the building fabric and services; energy rating, Fire Safety, Health & Safety compliance, room sizes, fixtures, facilities, finishes etc. Future alterations and projects can be planned and kept up to date. Data can be controlled and limited between different Stakeholders and user groups depending on their needs. The whole aim of the digital twin is to improve efficiency, reduce waste, and to ensure assets are safe and compliant with current and future requirements. In terms of the baseline aim, I guess it would be to create a 3d digital twin of several buildings on the campus with data input of the existing energy and condition rating (usage, cost, etc). Then using AI to evaluate the different options of improvements to the building with the aim of reducing the future maintenance and running costs. For example, Option 1 – thermal upgrade to the building fabric (roofs, walls, glazing etc) Option 2 - introduce or replace the existing heating installation Option 3 – reconfiguration of the building layout or several rooms which may result in reduced maintenance and energy cost And so on. The digital twin could demonstrate each option virtually to enable stakeholders to decide on the best option before actual implementation. | HML Associates Limited |  | Andrew Calway
14 | Biofilm simulator tool | This project will develop a digital tool to explore different biofilm treatments. A bacterial biofilm is a multicellular community of bacteria. They have been likened to our own multicultural cities, with individuals cooperating and competing within a complex system which is more resilient to stress. They also exhibit unique and interesting collective behaviours. Biofilms cause most clinical infections. They are notoriously resilient and difficult to control owing to several strategies, including their heterogeneity and tolerant sub-populations. We have developed agent-based models to develop optimized treatments for biofilms. Our simulations can currently be run in NetLogo to explore and visualise therapies. Biofilm growth and a biofilm’s behaviour and its response to a given treatment are dependent on a range of mechanisms and its environment. There is a vast parameter space associated with different treatments, strategies, biofilms, and scenarios. Clinicians or experimentalists wishing to find or develop optimized treatments for a given scenario, or strategy for a given treatment would benefit from an easily accessible digital tool that allows them to simulate and visualize different situations, biofilms and treatments. The aim of this project is to develop such a tool. | University of Bristol | Seth Bullock | Simon Lock
15 | Community Dashboards with Knowle West Media Centre | Community Dashboards https://kwmc.cloud/community-dashboards Currently we're building the groundwork for this system using our digital manufacturing space (The Factory) as the use case. Using Django, Vue and Tailwindcss, this will be an open-source modular system, which can be used and adapted for other community spaces. The project would involve meeting with community spaces to envision and co-design new modules to be featured on their dashboard. This could be showing how much energy their PV has generated each day, what the local air quality is, the estimated arrival time of the next bus etc. Essentially, thinking through what kind of data would be relevant to a place, how to make a generalised module for said data type, sourcing the data, and then designing an engaging representation of the information. We want to see creative representations of data, making information sourcing reliable and relevant, and lateral thinking to make modules extensible and not too niche or tied to an individual location. | Knowle West Media Centre | Paul Marshall | Aisling O'Kane
16 | Image Analysis using Mapillary to automate mapping for a Beat the Street game | Beat the Street is a programme of community engagement which culminates in a game for the whole community to participate in. The objective of Beat the Street is to tackle the issues of physical inactivity in communities as well as build social cohesion through the game and associated events. So far we have had over 1.6 million players participate across the UK. The locality is gamified using our Beat Boxes (Custom RFID card readers with a data connection, installed on lampposts) and cards with events surrounding the game lasting for 6 weeks. Teams in the game can be schools, community groups or businesses and they compete by walking between the Beat Boxes to score points for their efforts. The winning team is the one who scored the most points on the leaderboards by the end of the game. One of our most time consuming operations during Game setup is the discovery, mapping and on site risk assessment of appropriate lampposts to install our Beat Boxes on. For a typical game we may have 200 Beat Boxes installed on lampposts. Each lamppost must be 500 metres (routing distance) apart, with wide enough pavements that school children can safely access our Beat Boxes whilst playing the game. This project would like to explore: How might we use street level image data captured by a camera and processed by Mapillary (https://www.mapillary.com/) to automate or enhance the discovery and selection of appropriate lampposts within a specific game boundary, e.g. a small town. - Can we identify the type and dimensions of a lamppost, width, height and shape? - Can we identify useful constraints from the available data to make better decisions when selecting a lamppost? - Can we analyse the depth and accessibility of the pavement around a given lamppost? - Can we automate mapping of [x] lampposts within a given game boundary ensuring all chosen lampposts are approximately 500 metres (routing distance) apart, where [x] is total Beat Boxes in a game - Can we make any conclusions to help our risk assessment for installing a Beat Box at a given lamppost? - What cameras are best suited to data capture for our use case? About Mapilliary: Capture, upload, and use street-level imagery and data. Contribute imagery, manage map data, and bring it all to your mapping and GIS workflows with our apps and tools. We are currently using QGIS with a Google Street View plugin to perform desktop mapping of a given area before an on site risk assessment. Overview of existing process using QGIS to select lampposts: Schools are mapped first, with each school getting a Beat Box positioned outside each school entrance. Use QGIS Network Analysis tool to discover routes within 500 metres from a selected point (currently only including roads), to ensure the route between selected lampposts are approximately 500 metres apart. Use the QGIS QuickOSM plugin to help locate Beat Boxes near desired Points of Interests and amenities, e.g. Playgrounds, green spaces, cycle routes, museums and libraries. Example final map for game players can be seen here: https://www.beatthestreet.me/paisley/map/ | Intelligent Health Ltd | Andrew Calway | Jon Bird, Michael Wray
17 | Skills Exchange Community | Bristol Energy Network (BEN) is a network of over 35 community organisations as well as individual citizens, working to address challenges of energy transition to NetZero as well as energy poverty and equitable access to energy within Bristol and surrounding areas. All of these activities are closely linked with educating citizens on topics of renewable energy, retrofit and tackling energy poverty. One of BEN's key areas of work is helping communities to set up energy generation infrastructure (e.g., wind turbine in Ambition Lawrence Weston, or PV arrays, etc.), as well as help people learn and improve across all aspects (e.g., how to deal with rising energy prices within limited home budget, how to engage with novel energy services, such as demand side management, etc.). BEN is often asked to provide support for all manner or projects in and for communities, so BEN staff needs to manage a large volume of information, such as which members have what previous experience and skills, who can share the information requested for a current project on basis of previously completed project, who needs what training in which skills and where could such a training be received, etc. The present project will develop a knowledge collection and management infrastructure for BEN and community users. To explain the expected functionality through example, imagine that Bristol Energy Cooperative (BEC) (which has a strong experience of cooperative energy management projects) says they can deliver training on cooperative energy management project initiation and set up. At the same time, the Lawrence Weston community wants to set up a cooperative project. So, through the Project System: 1) BEC will record which training activities they are willing to provide, how long the training requires, if it is free or requires payment, etc. 2) Lawrence Weston community will be able to search for cooperative set up training and find BEC as a provider. 3) Functionality for training delivery request and negotiation needs to be developed, whereby a training date, method (e.g., workshop, video conference, etc.), conditions, etc. are agreed. 4) Training providers and receivers will then be able to post feedback/ratings post-training provision. Note that some training resources can be free (e.g., youtube videos, etc.) and BEN officers should be able to add these as relevant training materials. Other training may include courses delivered by colleges or non-community organisations too. Discussion and Q&A functionality will be very useful too. | Bristol Energy Network | Ruzanna Chitchyan | Inah Omoronyia
18 | Virtual Hospital Africa - Nurse application | PLEASE VIEW NURSE APPLICATION PROPOSAL HERE: https://bit.ly/40QisPn My name is Jonathan Tagarisa. Founding Trustee of Health Gateway Africa Trust. Our Trust is a health trust which is into WASH activities and health system strengthening programmes. You can view some of our work here: https://www.healthgatewayafrica.org Currently, we have an ongoing initiative whose aim is to build a Virtual Hospital that will make it possible for remote and underserved patients to access doctor and specialist care. Problem We noticed how difficult it is for remote and underserved communities in Southern Africa to access quality healthcare as well as receive continuous care. Mainly because of the distance between communities and hospitals. Non-availability of skilled personnel like doctors and specialists is also a huge issue. Situation was worse during the Covid pandemic as hospitals were in accessible for those with other conditions like Non Communicable Diseases and some were in isolation because if Covid itself. Solution Our solution is to build a Virtual Hospital with a portal at every primary health clinic or nearest health center to provide access to doctors and specialists. Action We opened a slack workspace where we have invited Software Developer volunteers to contribute their time helping to build the software. Amazon Web Services (AWS) has shown willingness to provide us with cloud services and other technologies to host the hospital. An organisation called Toptal, toptal.com, provided us with a Project Manager, A Project Architecture and a Project Owner . The Virtual Hospital will be deployed to remote and underserved areas where traditional hospitals are either unreachable or unaffordable. The Virtual Hospital will consist of the following modules: 1. Patient Application 2. Nurse Application 5.2.2 Nurse ApplicationThis is one of the most important modules on the Virtual Hospital. This application will be provided to a Nurse who can be stationed anywhere from a rural clinic to an educational institution. It will be the entry point for most patients into the Virtual Hospital system. The nurse can register patients as well as use POCT integrated devices to help with diagnostics. They can also investigate and examine patients with the resultant information posted to the cloud where authorized Virtual Doctors can review the information and come up with a treatment plan. The application will also provide effective follow ups as nurses will be at the forefront of interacting with the Virtual Doctors. 3. Virtual Doctor Application 4. Community Health Worker/Caregiver Application. 5. Virtual Ward 6. Whatsapp chatbot to facilitate interaction with third party service providers like Pharmacists, Laboratorists, Radiographers and other Specialists. 7.Bluetooth Enabled Diagnostic Devices and Point Of Care Testing The project is an ongoing project as more tools are added and a Proactive Healthcare application for screening diseases is to be considered in the future. Current Challenges • The Software Volunteer developers are unable to commit enough time to get the project off the ground because of other paid commitments they would have made. Interventions Required Software Developers with a passion for humanity willing to assist with their time to see the project through. At least up to MVP stage. | Health Gateway Africa Trust |  | Inah Omoronyia
19 | Populating a database to be loaded to smartwatches for behavioural testing | Ecological Momentary Assessment (EMA) is a technique used in psychology research to collect data from individuals over a period of time, by presenting them with repeated questions at specific time intervals and recording their answers. Put simply, it's like sending them a short questionnaire or a survey about their current behaviour or circumstances, which they complete in real time in their everyday environment. This allows psychologists to collect ecologically valid (i.e. naturalistic) data about people instead of having them come into the laboratory and carry out tests in controlled but unrealistic conditions. Traditionally, ecological momentary assessment is carried out by smartphone apps, but in the School of Psychological Science we have developed a system which performs EMA on a smartwatch. Using a smartwatch enables a more immediate and less burdensome presentation of the EMA questions and is quicker and easier for participants to submit their responses. The questions and responses are stored in a database within the smartwatch's internal memory. Currently, the EMA questions are added to this database using a database browser, and the database is uploaded to/downloaded from the watch using a script containing Android commands. This works, but is cumbersome. So that the system can be used more easily by researchers, we need a quick and easy way to populate the database with the researcher's desired EMA questions and upload it to the smartwatch, and then download the database from the smartwatch when the participant has finished entering their data. Ideally this should be a website or web-based system which the researcher could access from anywhere without the need for a dedicated computer or installation of specialist software to enable data transfer to and from the smartwatch device. (For additional information - I have a background in the software development industry and would be happy to evaluate and provide feedback on the professionalism and quality standards of the student's approach to developing a solution). | School of Psychological Science, University of Bristol | Sean Froudist-Walsh | Paul Marshall
20 | Project Management Game | Overall goal I’d like to create an online simulation version of a ‘game’ we have been using in teaching project management. (NOTE: we can provide the seminar brief for the existing game for e a more detailed starting point) Background For several years, we have been using Lego to introduce concepts and practicalities of project management for undergraduate and postgraduates studying our project management units. This has usually been deployed as a one-off in an introductory seminar. Using the ‘Lego Challenge’ has been effective and enjoyable, but is constrained by physical limitations of Lego play. An online sim/game would provide a platform for wider use in more contexts, for instance as part of group work, rather than a one-off or ice breaker. Scope in more detail Individually or in groups, students would plan and execute their projects to produce a deliverable (typically a constructed building). The purpose is for students to practice applying project management concepts/theory to a ‘real’ project, and to hone team-working skills, and to develop their ability to cope with risk, complexity, and change as the project evolve ‘in reality’. We can supply the learning activity (seminar brief) for our Lego Challenge as a starting point for turning this into an online sim/game (minus the Lego brand, obviously!). The initial version could simply more or less implement the simple ‘design and build a tower’ conceit, but further versions could add features for more flexibility in managing the project. The required parameters, inputs, and outputs are: Must-haves Instructor input 1. Set dimensions of the target ‘product’ (initially a simple building, such as a tower): height range, colours, footprint area, etc. 2. Set time limits on how long students have in various project phases (definition, design/plan, procurement, execution/build, reflection) 3. Unit cost of materials and time (bricks of different kinds, labour); these might change due to ‘market conditions’ during the game 4. Other features required by the client (which may change during the game, e.g., add a helipad) 5. Random ‘events’ to keep the teams on their toes (e.g., changes in internal or external forces) Student input 1. A basic design plan for the deliverable, e.g., height and footprint of building; construction materials to be used; team roles for different responsibilities 2. Identify activities to be done and sequence them 3. Monitor progress and control the project (make adjustments, e.g., to schedule, resources, scope) 4. Communication with each other and sponsor/client Game output 1. Project progress report based on student inputs, i.e., cost and schedule and scope achieved based on implementation of design/plan; comparison against plan 2. Ideally some visual representation of progress of the deliverable 3. Alerts on problems needing attention (e.g., labour strike, lack of resources, going over budget) 4. Alerts when required activities have not been actioned or scheduled, e.g., missing materials procurement phase or missing quality control activities 5. Communications channel and log for team and instructor interactions Should-haves (longer term?) 1. Students can create a work breakdown structure of activities, and sequence these as their work plan 2. The system works out the critical path based on the activity network 3. The system produces a Gantt chart based on the activity network and resources allocations; students use the chart to monitor schedule performance | University of Bristol Business School | Simon Lock | David Bernhard
21 | Assisting fast fashion become circular | Context The fashion industry is the second most polluting industry, behind oil and gas (Qutab, 2017), generating an abundance of environmental impacts (Niinimäki, et al., 2020). Waste production within the fashion industry is significant and has shown to drastically increase, up 44%, since the Covid-19 pandemic (ACS, 2022), contributing further to the 92 million tonnes of clothing ending up in landfill every year (Igini, 2022). With our clothes being cheaper than ever (Denby, 2021), there has been a shift in societal views and habits towards purchasing clothing, evidenced as a ‘the average person buys 60 per cent more items of clothing every year’ (Constable, n.d.). With a surge in online shopping, clothing returns could be considered the fundamental cause with, 50% of returns never making it back onto the shelves (ACS, 2022). Whilst returns generate negative environmental affects, they also show to largely detriment clothing companies profit margins, with returns costing £7 billion a year for UK retailers (The Times, 2022). Despite companies, such as ACS (2022), aim at mitigating the immense volume of clothing waste through regenerating clothes, a gap remains in the market for a low-priced, quick, and simplistic way for clothing retailers to reduce their wastage and costs. Therefore, we have identified a way to mitigate these macro-scale environmental effects caused by this industry, whilst reducing returns costs for clothing retailers. By providing an app that can be used directly by these clothing companies to sell their damaged, unsellable products quickly and at a bargain price, to then be picked up the same day by app users, will benefit both the clothing company and fashion consumers. Our Vision The vision is simple, being able to provide cheap clothing to a wide range of consumers whilst helping put the plug on the rising issues of waste emissions caused by the world of fashion returns. Our Mission Our mission is to significantly reduce the waste from high street clothing brands through the sales of their returned products that otherwise wouldn’t have made it back on shelves whether they’re damaged, stained or just not suitable to sell ‘as new’. Audience - Clothing companies- Due to high costs from returning packages with no company benefits, our company provides a way for these companies to make a revenue from these unsellable returns, whilst making their company more sustainable. - Fast fashion purchasers- These individuals can use our company for access to their favourite fast fashion companies but, for much cheaper prices and to be more sustainable. - Environmentally aware individuals- Our company reduces the amount of clothes that are thrown away, thus, reducing the levels of fashion waste and pollution. Therefore, individuals who are aware of this fashion waste problem can utilise it to assist in eradicating this environmental issue. - Low disposable income individuals- Individuals who don't have the disposable income to purchase certain high street fashion can use our company to purchase fashion which is trending for low prices. Also, due to the current financial crisis, there is a large decrease in disposable income nationally. Therefore, our company assists the national population stay fashionable throughout this crisis. Impacts Our aims and target section demonstrates the benefits our company has on reducing fashion waste and improving the sustainability of clothing companies. However, our company could also lead to a paradigm shift in societal views around fast fashion. Fast fashion is set to rise to unimaginable heights within the coming years (Hosey, 2020) therefore, its eradication may be an unfeasible target. Our company will educate through increasing awareness of fashion waste and reduce people from buying fast fashion brand new. *Contact for references*
22 | Rainforest Records | The Bristol Rainforest is a not for profit group of volunteers that places Rainforest trees in classrooms across Bristol and beyond. Children are told about Rainforests and are taught how to look after the trees they are given. They record their tree's growth and to share their pictures with us and other schools. We then have a record of trees over many years. These records are instructive in learning how trees grow and allow children to follow the progress of their trees once they have moved schools. The work of collating pictures is becoming very unwieldy and time consuming and we would love to automate the process. We would value a system which enables children in schools to take a picture of a tree to be taken and for that picture to be automatically uploaded to a specific folder on our personal cloud store. An Android app that allows a QR code on the pot of a tree to be scanned then allows a picture to be taken. It then uploads that picture to the folder detailed in the QR code. Or perhaps the QR code could be used to get a folder address from an associated database. Such a system may well have many other general uses too. Keeping photographic records would be useful in many other situations. As the ease of taking pictures has increased the difficulty in staying on top of filing them has increased too. Industries such as horticulture, forestry and construction that need to keep photographic records of plants or components would find a simple app to automatically sort pictures useful too. **Important that the organisation retains IP from this project** | The Bristol Rainforest |  | Jon Bird, Seth Bullock
23 | Cribster | Team: Daniel Virin, CEO (Economics and Politics BSc), Laurence Li, COO (Economics BSc), Joe Checkley, CFO (Economics BSc), Nyse Vicente, Head of Design (French and Russian) We are a team of students who, after watching the student housing crisis and facing countless housing issues, decided to make matters into our own hands. We are designing an app to help people find flatmates and properties during the current housing crisis. You can find us individually on LinkedIn (or on the group page: Cribster UK) to ask any questions: https://www.linkedin.com/company/cribster-uk Introduction: In 2019/20, there were over 900,000 students looking for a rental property in the UK. In a clever interface wrapped within a mobile app, Cribster will provide a platform for students to easily identify their ideal housemates and houses. Landlords may connect with students who meet their criteria. This report will primarily focus on the Bristol region, where the co-founders study, however, we plan to expand Cribster to the entirety of the UK. The problem: We see the student property market as flawed for two reasons: 1. Students often struggle to find suitable extra tenant/s so they can sign for a property 2. Landlords often struggle to match with students who match their preferences This results in market failure, where both parties (students and landlords) are left unsatisfied and a considerable amount of time is wasted. This is being exacerbated by the student housing crisis that is developing across universities, with more students attending University every year and an ill-equipped housing market. The Solution: Cribster will ask users to build profiles, with verified profile photos, providing information on what we have identified as key categories: • Age • Gender • Year of Study • Course of Study • Hobbies • Budget • If they drink • The location they wish to live in Cribster users will then be able to make posts in the app, perhaps looking for flatmates or someone to take over their current tenancy. Users will be able to search through, and filter these posts, based on the above key profile categories. Once a potential post has been identified, users can click on the poster's verified profile to attain more information. They will also be able to message the user within the app e.g., to schedule a phone call or meeting. We are initially focused on matching students, and intend to transition into matching students to properties in the future. This will entail showing available listings and allowing students to message estate agencies within the app. Our idea has been described as ‘The Tinder for Finding a Flatmate’ by Justin Basini (CEO of ClearScore), an advisor to the company. Market Validation: We have personally undergone the process of looking for housemates and signing on to a property, and have recognised that this ordeal is riddled with issues. This view is commonly shared among students in Bristol, and students nationwide. We have proven this by conducting market research in the Redland and Clifton area: • 90% of students surveyed relied on an external platform such as Facebook or the Bristol University Forums. • Not a single student thought the current process was satisfactory. • 100% of students stated that they found the current process anxiety-inducing. Plan: Once assigned to a team of students in the Software Engineering department, we will meet with them to pitch our vision in person and understand the specific skills they can bring forward to the project. The current Cribster Team will produce wireframes of our vision for what the application will look like, and the different windows within it. We will show these to the students, and ask for their feedback to create a more finalised design. Once the User Interface has been established, we want the students to work on a functioning prototype of our application. It should have the following functions: Once we create a User Interface design, we want the students to work on a functioning MVP prototype: • Downloadable in the App Store/Google Play (or waiting list) • Ability to make a user profile • Ability to message other users • Ability to post, and filter through posts • Integrated Colours and Branding • About Page • Contact page Within the scope mentioned above, coders can add and suggest their own artistic vision to the project. We appreciate the scale of this task, however, our research suggests a basic application can be coded in a straightforward way via platforms such as Figma (using servers like Firebase). We want coders who are passionate about the issue at hand, which has affected the well-being of thousands of students. We also intend to give equity in our business to each of the students that join the project as an incentive - this can be discussed further. We will have a hands-on approach and remain disposable to answer any questions that you may have. | UoB |  | Seth Bullock
24 | Peer to Peer Gig Booking Application | Peer-to-peer home services, also known as sharing economy services, have gained popularity in recent years due to their convenience and cost-effectiveness. These services allow individuals to offer their skills and services to others in their community, while also providing an opportunity for those in need of services to easily find and connect with local providers. In order to facilitate this process, we propose the development of a mobile app that connects individuals who are offering home services with those who are seeking them. This app would allow users to browse and book services, communicate with service providers, and make secure payments all from their phones. Features: > Service listings: Users can browse and search for services in their area, including options such as housekeeping, landscaping, handyman services, and more. > Service provider profiles: Service providers can create a profile that includes information about their services, pricing, availability, and ratings/reviews from past customers. > Messaging: Users and service providers can communicate directly through the app to discuss details of the service, such as scheduling and specific tasks to be performed. > Secure payments: Users can make payments through the app using a secure payment system, eliminating the need for cash transactions. > Rating system: After the service is completed, users can rate and review their service provider, providing valuable feedback for both the provider and other users. Benefits: > Convenience: The app would allow users to easily browse and book services from their phone, saving them the time and effort of searching for and contacting service providers manually. > Connects local communities: By connecting individuals in the same community, the app would foster a sense of community and support local businesses. > Enhanced security: The app's secure payment system and rating system would provide users with added peace of mind and help ensure a high quality of service. Conclusion: The development of a peer-to-peer home service mobile app has the potential to greatly benefit both service providers and users. By providing a convenient and secure platform for connecting and booking services, the app would streamline the process of finding and booking home services. We believe that this app would be well-received by both service providers and users, and would become a valuable resource for facilitating home services in local communities.
25 | Mayden case study - create online interactive webpages | To create a webpage which is interactive for an online teaching case study from data already collected. I have films, photographs, documents, emails, articles, weblinks, interviews etc. that make up data collected from a Bath based IT company (Mayden), which I want to make available on a webpage/intranet site. I would like the students to experiment with different ways of presenting this data so as to allow for student interaction. I don't have IT experience but I can design and generate ideas with them based on my subject knowledge and teaching experience, then allow them to translate this into a functioning webpage. The final product could easily be tested out on UofB students. The company is interesting because of the way that they organise themselves as an 'holocracy' which means they are self organised in teams based on Agile and coaching principals. This will be interesting to a student wanting to work in any high tech company as Agile practices are common place. I would expect to include the students' name on the webpage if it becomes published. I have space in my office (Howard House) if the students needs a base to work from. I am a part-time Lecturer within the University of Bristol with 20+ years experience, and teach management subjects - mainly strategy. | University of Bristol Business School |  | Simon Lock