## Potential Licsencing Tools
Type | Name | Purpose | Usage Extent | Funding | Standard (staff) Windows desktop | Open Access | Staff Remote Desktop | Student Remote Desktop | Lecture Theatres | Supplier | BYOD Staff | BYOD Students | Licensed Users | Status
framework | .net
IDE | jetBrains
Editor | Latex
LaTex pdf viewer | Texmaker
IDE | Visual Studio
Code Editor | Visual Studio Code
Office Tools | Microsoft Office
Programming Language | Python
Programming Language | Java
QuickTime
IDE | Rstudio
Meeting tools | Skype
Timetabling | Syllabus Plus
Data Analysis and Graphing | Tableau
Game Engine | Unitity

## Timetable
May | June |  |  |  | July |  |  |  | Aug |  |  |  |  | Sep
wk16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30
Preparasion Software Tools | Questionnaire (Confirm Requirements) & Prototypes |  | Sprint 1 |  | Confirm 1st Sprint Results | Sprint 2 |  | Confirm 2nd Sprint Results | Sprint 3 (Include code Testing, User Experience , Optimization) Start working on Group / Individual report |  | Finalise the application | Group Report Finished | Individual Report Finished | Submission 5th,Sep | Vivas 5,Sep - 12,Sep
Project Introduction & Preparation
wk16
2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04
| 1.Finalised Questionnaire 2.Draft Functionalities & Features 3.Project Timetable 4.Potential licensing tools | 1.Final version of Questionnaire - Create Link 2.A list of potential licensing tools 3.Finalise Project TimeTable 4. Use case - individual |  | 1.Finalize use-case diagram 2.check final questionnaire |  | First Report: 1. Questionnaire - link 2. Use case diagram 3. Ethic declaration 4. Pontential Programming Language and tools 5. Github / Jira Links to monitor progress
May wk16: wk17; July WK23: wk18; Sep WK30: wk19 | [6 empty] | wk20
2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02
Start |  | 1 Work on prototype of application | [6 empty] | 1.Collecting & Analyzing collected data from Questionnaire |  | 1.Final version of use case diagram 2. Decide programming languages 3.Send for approval for requirements base on questionnaire 4.Send for approval for prototype |  |  | SPRINT 1
wk21 | [6 empty] | wk22 | [6 empty] | wk23 | [6 empty] | wk24
2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30
1st sprint results check | [6 empty] | Sprint 2 | [6 empty] | Sprint 2 | [6 empty] | checking 2nd sprint |  | Presentation and Evaluation Skills workshop
Report Skills workshop
wk25 | [6 empty] | wk26 | [6 empty] | wk27 | [6 empty] | wk28
2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06 | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27
Start Group & Individual Report | Sprint 3 | [5 empty] | Sprint 3 | [6 empty] | Finalising Group Report & Individual Report
wk29 | [6 empty] | wk30
2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10
[8 empty] | Hand In Report | Vivas(5,Sep to 12,Sep)